## Kettle 8.3 Conversion Steps
Steps | Refer
Download kettle 8.3 | Follow steps from the following document : svn://svn-staging.maximus.com/dev1d/maxdat/trunk/kettle8/Doc/Kettle_8.2_Runbook_20190827
Create a master Kettle 8.3 conversion ticket in Jira for the project - Please refer | NYHIX-51968
Create subtask under the master ticket for installing Kettle 8.3 on the app server. | NYHIX-51969
Create subtasks under the master ticket for creating kettle8 directories on the app server | NYHIX-52026
Create appropriate folder structures in SVN | Example : svn://svn-staging.maximus.com/dev1d/maxdat/trunk/kettle8/NYHIX
Copy all the code from PROD App server onto your local machine
Check KTR files to replace tablename with uppercase letters.
Open up ktr and kjb files using Kettle 8.3 and save them locally on your machine
Download Config files from the app server
Make modifications to Kettle.properties, shared.xml and .set_env
Replace clear text passwords with encrypted passwords in kettle.properties | Follow step 2 in NYHIX-53417
Make necessary changes to script to point to .set_env files and add appropriate modules
Install cygwin for running Dos2Unix commands
Run dos2unix command on all the converted files before moving the files onto DEV App server | Command to run : find ./ -name '*' -maxdepth 10 -exec dos2unix {} \;
Copy all the converted files to appropriate kettle8 folders on SVN
Create subtask under the master ticket for app admins to move the code and config filesfrom SVN onto the Dev App server under the appropriate Kettle 8 directories
run test_connection script to make sure the connections are working fine

## Issues Faced during Conversion
Issue | Notes
Install right ojdbc.jar file based on the appropriate Oracle version
Change permissions of ojdbc7.jar file | NYHIX-52921
JDBC.properties files missing | NYHIX-52823
Cachejdbc.jar file missing | NYHIX-53049
Permission issues with pdi.log file | NYHIX-53049
Ran into issues with ktr files not pointing to the right folder due to folder restructuring for NYHIX project | Point the ktr and kjb files to the right folder structure if needed
Issues with Truncate and load option on Table output step in ktr | Uncheck Truncate and load option on Table Output step and add a Execute script with truncate step at the beginning of the transformation. Example : svn://svn-staging.maximus.com/dev1d/maxdat/trunk/Kettle8/NYHIX/MailFaxBatch_Stg_Central_OLTP_BATCH_EVENTS.ktr
Issues related to script changes | Fix scripts
Log files not created in the right folder | Fix scripts